## RA Summary
Risk Assessment No.
Reason for RA:
Type of RA
Location:
Date:
Attendees | Title / Role
Scope and Context - what is this about? What are we trying to achieve? Background? What's in & what’s out of scope?
Example

## RA Template
1. Identify Risks |  |  | 2. Analyse Risks |  |  |  |  | Current Risk Level Of worst credible safety consequence, considering existing controls |  |  | 3. Evaluate Risks |  |  | 4. Treat Risks |  | Anticipated Risk Level Of worst credible safety consequence, after treatments are introduced
[5 empty] | Existing Controls | [5 empty] | Potential Treatments
ID | Risk Description What could go wrong? | Risk Owner Who is accountable for managing this risk? | Cause(s) What could cause this risk to occur? | Consequence(s) What are the potential impacts of the risk on the organisation & people involved ? | Control Description(s) What do we do now to manage the risk? | Reference to SMS Where can more detail on the control can be found? | Control Owner Who is responsible for implementing this control? | Likelihood | Consequence | Level of Risk | Treatment description What else can be done to manage this risk? | Treatment decision Are the potential treatments resonable or not? Why? | Risk Status Can we accept this risk or not? | Treatment Owner Who is responsible for introducing this treatment? | Treatment Due Date | Likelihood | Consequence | Level of Risk
1 | Derailment of passenger train | A. Person | 1. Broken rail 2. Axle failure 3. Overspeed round bend | 1. Harm to driver and passengers 2. Reputational damage 3. Damage to track | 1. Track maintenance 2. Rolling stock maintenance 3. Driver route knowledge | 1. Track Maintenance Plan (TMP1) 2. Rolling Stock Maintenance Plan (TMP2) 3. Route knowledge diagrams and training records (REF123) | 1. A. N. Other 2. S. O. Else 3. A. N. Other | Unlikely | Catastrophic | Medium | 1. Increase frequency of track inspections 2. Check driver training records | 1. Reject - Resources unavailable 2. Accept | Treat | 2. A. N. Other | 2020-05-01 | Very Unlikely | Catastrophic | Low
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
Example

## Risk Matrix
Insert Risk Matrix (Consequence, likelihood, risk rating & action tables) for easy reference

## Drop Down List
Type of Risk Assessment | Reason for Risk Assessment | Location / Asset | Likelihood | Consequence | Level of risk | Risk status
Change Management |  |  | Very Unlikely | Insignificant | Low | Under consideration
New | Change to process or procedure | Office | Unlikely | Minor | Medium | Accept / SFAIRP
Review | Interface Agreement | Road Crossing - Private | Likely | Moderate | High | Treat
| Maintenance - Rollingstock | Road Crossing - Public | Very Likely | Major | Extreme | Closed
| Maintenance - Rail Infrastructure such as track and signals | Rolling stock | Almost Certain | Catastrophic
| Operations | Station / platform
| Project | Track / rail infrastructure
| Change to organisational structure or governance | Workshop
| Change to legislation / regulatory change | Sheds
| Incident or accident | Turntable
Periodic review
Attendees
Accountant
Board Member
Contractor
HR Manager
Rail Safety Worker, such as drivers, infrastructure maintainers, rolling stock maintainers or restorers
Risk Manager
Safety Manager
Workshop Manager
Operations Manager
Track Manager
Supervisor