## Risk Register Template
| 1. Identify Risks |  |  | 2. Analyse Risks |  |  |  |  | Current Risk Level Of worst credible safety consequence, considering existing controls |  |  | 3. Evaluate Risks |  |  | 4. Treat Risks |  | Anticipated Risk Level Of worst credible safety consequence, after treatments are introduced
[6 empty] | Existing Controls | [5 empty] | Potential Treatments
Risk Assessment No. | ID | Risk Description What could go wrong? | Risk Owner Who is accountable for managing this risk? | Cause(s) What could cause this risk to occur? | Consequence(s) What are the potential impacts of the risk on the organisation & people involved ? | Control Description(s) What do we do now to manage the risk? | Reference to SMS Where can more detail on the control can be found? | Control Owner Who is responsible for implementing this control? | Likelihood | Consequence | Level of Risk | Treatment description What else can be done to manage this risk? | Treatment decision Are the potential treatments resonable or not? Why? | Risk Status Can we accept this risk or not? | Treatment Owner Who is responsible for introducing this treatment? | Treatment Due Date | Likelihood | Consequence | Level of Risk
RA1 | 1 | Derailment of passenger train | A. Person | 1. Broken rail 2. Axle failure 3. Overspeed round bend | 1. Harm to driver and passengers 2. Reputational damage 3. Damage to track | 1. Track maintenance 2. Rolling stock maintenance 3. Driver route knowledge | 1. Track Maintenance Plan (TMP1) 2. Rolling Stock Maintenance Plan (TMP2) 3. Route knowledge diagrams and training records (REF123) | 1. A. N. Other 2. S. O. Else 3. A. N. Other | Unlikely | Catastrophic | Medium | 1. Increase frequency of track inspections 2. Check driver training records | 1. Reject - Resources unavailable 2. Accept | Treat | 2. A. N. Other | 2020-05-01 | Very Unlikely | Catastrophic | Low
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
Copy and paste the contents of each risk assessment into one document to create a risk register.
Enter the name or number of the risk assessment being copied over.
You can then sort by Level of Risk (column L or column T)
An example is included in red in row 4.
Example

## Drop Down List
Likelihood | Consequence | Level of risk | Risk status
Very Unlikely | Insignificant | Low | Under consideration
Unlikely | Minor | Medium | Accept / SFAIRP
Likely | Moderate | High | Treat
Very Likely | Major | Extreme | Closed
Almost Certain | Catastrophic
Example